## Resource
Resource Name | Type | Initials | Group | Max. Units | Std. Rate ($/hr) | Ovt. Rate ($/hr) | Accrue At
Document Controller | Work | D | Document Management | 100% | 32 | 42 | Prorated
Project Management Team | Work | PMT | project Management | 100% | 500 | 600 | Prorated
Electronic Technician | Work | ET | Facility | 100% | 18 | 28 | Prorated
Reliability Engineer | Work | R | Engineering | 100% | 40 | 65 | Prorated
Mechanical Technician | Work | M | Facility | 100% | 18 | 28 | Prorated
Structural Engineer | Work | S | Engineering | 100% | 35 | 45 | Prorated
Instrumentation Engineer | Work | I | Engineering | 100% | 35 | 45 | Prorated
Systems engineer | Work | S | Engineering | 100% | 40 | 50 | Prorated
Safety engineer | Work | S | Engineering | 100% | 40 | 50 | Prorated
Product Engineer | Work | P | Engineering | 100% | 40 | 50 | Prorated
Project Controller | Work | P | Project Management | 100% | 40 | 50 | Prorated
Procurement Engineer | Work | P | Supply Chain | 100% | 38 | 48 | Prorated
Vendor | Work | V | Other | 100% | 0 | 0 | Prorated
Painter | Work | P | Facility | 100% | 18 | 28 | Prorated
Asthetic Designer | Work | A | Facility | 100% | 18 | 28 | Prorated
Laborer | Work | L | Facility | 100% | 10 | 20 | Prorated
Technicians | Work | T | Facility | 100% | 18 | 28 | Prorated
Quality Engineer | Work | QE | Engineering | 100% | 30 | 40 | Prorated
Welder | Work | W | Facility | 100% | 15 | 25 | Prorated
Electrical Engineer | Work | EE | Engineering | 100% | 40 | 50 | Prorated
Mechanical Engineer | Work | ME | Engineering | 100% | 40 | 50 | Prorated
Project Manager | Work | PM | Project Management | 100% | 60 | 70 | Prorated
Foreman | Work | F | Other | 100% | 0 | 0 | Prorated
Stakeholders | Work | S | Other | 100% | 0 | 0 | Prorated
Sponsor | Work | S | Other | 100% | 0 | 0 | Prorated
Accountant | Work | ACNT | Finance | 100% | 30 | 40 | Prorated
Technical Writer | Work | T | Document Management | 100% | 28 | 38 | Prorated

## Activities
WBS | Task Name | Predecessors | Duration | % Complete | Resource Names | Start | Baseline Cost | Total Baseline Cost | Actual Cost | Total Actual Cost | Cost Varience
1.1.1 | 01 Scope definition |  | 3 | 100% | Sponsor,Stakeholders | 2018-06-01 | 0 | 0 | 0 | 0 | 0
1.1.2 | 02 Charter | 2 | 3 | 100% | Product Engineer,Project Manager | 2018-06-04 | 4800 | 4800 | 4800 | 4800 | 0
1.1.3 | 03 Charter approval | 3 | 6 | 100% | Stakeholders ,Sponsor | 2018-06-07 | 0 | 4800 | 0 | 4800 | 0
1.2.1 | 04 First cut technical design | 4 | 3 | 100% | Product Engineer | 2018-06-13 | 1920 | 6720 | 2040 | 7200 | 120
1.2.2 | 05 Electrical engineering | 5 | 30 | 100% | Electrical Engineer | 2018-06-16 | 24000 | 30720 | 26000 | 34500 | 2000
1.2.3 | 06 Mechanical engineering | 5 | 30 | 100% | Mechanical Engineer | 2018-07-13 | 24000 | 54720 | 26245 | 60745 | 2245
1.2.4 | 07 Structural engineering | 5 | 30 | 100% | Structural Engineer | 2018-07-16 | 24000 | 68500 | 28000 | 74500 | 4000
1.2.5 | 08 Final review | 8 | 5 | 100% | Product Engineer,Project Manager | 2018-08-15 | 8000 | 76500 | 8200 | 82700 | 200
1.2.6 | 09 Complete design documentation | 9 | 20 | 100% | Product Engineer,Project Manager | 2018-08-20 | 10000 | 86500 | 10521 | 93221 | 521
1.3.1 | 10 Master Bill of Material | 9 | 15 | 100% | Project Controller,Accountant | 2018-08-20 | 11500 | 98000 | 11552 | 104773 | 52
1.3.2 | 11 Parts ordered | 9 | 10 | 100% | Procurement Engineer | 2018-08-20 | 13000 | 111000 | 13548 | 118321 | 548
1.3.3 | 12 Procurement cycle | 12 | 60 | 100% | Vendor | 2018-08-30 | 13250 | 124250 | 13250 | 131571 | 0
1.4.1 | 13 Setup Asembly line | 9 | 45 | 100% | Electronic Technician,Technicians | 2018-08-20 | 14000 | 138250 | 18856 | 150427 | 4856
1.4.2 | 14 Power train | 14 | 10 | 100% | Electronic Technician | 2018-10-04 | 3840 | 142090 | 4325 | 154752 | 485
1.4.3 | 15 Frame | 14 | 15 | 100% | Welder,Technicians | 2018-10-04 | 7920 | 150010 | 8004 | 162756 | 84
1.4.4 | 16 Body | 14 | 10 | 100% | Laborer,Foreman | 2018-10-04 | 9500 | 159510 | 10045 | 172801 | 545
1.4.5 | 17 Instruments | 13 | 8 | 100% | Laborer,Foreman | 2018-10-29 | 4500 | 164010 | 4555 | 177356 | 55
1.4.6 | 18 Paint and Trim | 17 | 5 | 100% | Painter,Asthetic Designer,Laborer | 2018-10-14 | 7680 | 171690 | 8245 | 185601 | 565
1.4.7 | 19 Final asembly | 19 | 10 | 100% | Asthetic Designer,Laborer,Technicians | 2018-10-19 | 7360 | 179050 | 8242 | 193843 | 882
1.5.1 | 20 Test plan | 13 | 5 | 100% | Reliability Engineer,Quality Engineer | 2018-10-29 | 5600 | 184650 | 6452 | 200295 | 852
1.6.1 | 21 Power train testing | 16 | 12 | 100% | Electronic Technician,Reliability Engineer | 2018-10-19 | 12288 | 196938 | 12746 | 213041 | 458
1.6.2 | 22 Frame testing | 16 | 20 | 100% | Reliability Engineer[50%],Mechanical Technician | 2018-10-19 | 14880 | 211818 | 15735 | 228776 | 855
1.6.3 | 23 Body integrity testing | 17 | 10 | 100% | Structural Engineer | 2018-10-14 | 8000 | 219818 | 8555 | 237331 | 555
1.6.4 | 24 Instrument testing | 18 | 10 | 70% | Instrumentation Engineer,Reliability Engineer | 2018-11-06 | 14400 | 234218 | 22653 | 259984 | 8253
1.6.5 | 25 System testing | 25 | 10 | 0% | Systems engineer,Product Engineer | 2018-11-16 | 12800 | 247018 | 13800 | 273784 | 1000
1.6.6 | 26 Safety testing | 26 | 15 | 0% | Safety engineer | 2018-11-26 | 9600 | 256618 | 10457 | 284241 | 857
1.7.1 | 27 Admin close | 26 | 5 | 0% | Project Management Team | 2018-11-26 | 8000 | 264618 | 8858 | 293099 | 858
1.7.2 | 28 Project archivin | 26 | 5 | 0% | Document Controller ,Technical Writer | 2018-11-26 | 4800 | 269418 | 5384 | 298483 | 584
1.8.0 | 29 Project Management |  | 196 | 84% | Project Management Team | 2018-06-01 | 0 | 269418 | 0 | 298483 | 0
1.9.0 | 30 Project Close | 29 | 1 | 0% | Project Management Team | 2018-12-01 | 0 | 269418 | 0 | 298483 | 0
Formulas:
Start = [Start, row above]+[Duration, row above]
Start = G5+[Duration, row above]

## Summary
WBS | Task Name | Baseline Cost | Actual Cost | % Complete | Start | Baseline Total Cost | Actual Total Cost | Cost Varience
1.1 | Design | 0 | 0 | 100% | 2018-06-01 | 0 | 0 | 0
1.2 | Engineering | 49920 | 51420 | 100% | 2018-06-13 | 49920 | 51420 | 1500
1.3 | Procurement | 12048 | 12648 | 100% | 2018-08-20 | 61968 | 64068 | 2100
1.4 | Assembly | 27920 | 29920 | 100% | 2018-08-20 | 89888 | 93988 | 4100
1.5 | Testing | 5600 | 5900 | 100% | 2018-10-29 | 95488 | 99888 | 4400
1.6 | Component testing | 41128 | 41128 | 20% | 2018-10-19 | 136616 | 141016 | 4400
1.7 | Project close process | 20000 | 22960 | 0% | 2018-11-26 | 156616 | 163976 | 7360
1.8 | Project close | 0 | 0 | 0% | 2018-12-01 | 156616 | 163976 | 7360
1.9 | Project Management | 0 | 0 | 80% | 2018-06-01 | 156616 | 163976 | 7360